## Components
component | owner | status | due_date | priority | notes
flow_controller | alex.k | in_progress | 2026-06-15 | P1 | Sweep complete, awaiting reviewer signoff
pressure_sensor | morgan.s | complete | 2026-04-01 | P2 | Validated against ramp test
temp_regulator | alex.k | in_progress | 2026-06-30 | P1 | PID tuning ongoing, kp=1.5 recommended
voltage_monitor | jamie.t | blocked | 2026-05-30 | P2 | Probe shielding issue, hardware fix in flight
signal_buffer | morgan.s | in_progress | 2026-07-10 | P2 | Need to validate drop_policy=newest path
clock_divider | priya.r | complete | 2026-03-20 | P1 | All divisors validated, odd divisors documented
packet_router | jamie.t | not_started | 2026-08-15 | P3 | Awaiting upstream design freeze
queue_balancer | priya.r | not_started | 2026-08-30 | P3 | Spec under review
error_aggregator | alex.k | in_progress | 2026-07-15 | P2 | First-pass implementation done
audit_logger | morgan.s | complete | 2026-02-28 | P3 | Stable, no open issues